## WBS
PROJECT WORK BREAKDOWN STRUCTURE
No. | WBS Item | Complexity | Est. Effort (pds) | Deadline | Stage | Type
Stage 1 | Project Initiating |  |  |  | Stage 1 | Section
1.1 | Report 1 (Project Introduction) |  | 12 | Week 1 | Stage 1 | Deliverable
1.1.1 | Conduct business domain analysis and evaluate material leakages | Complex | 5 | Week 1 | Stage 1 | Completed
1.1.2 | Draft operational pain points and unmet need summary | Simple | 3 | Week 1 | Stage 1 | Completed
1.1.3 | Consolidate and baseline Report 1_Vision_Scope_BPG-CMS.docx | Medium | 4 | Week 1 | Stage 1 | Completed
Stage 2 | Project Planning & Initial Requirements |  |  |  | Stage 2 | Section
2.1 | Report 2: Project Management Plan v1.0 |  | 10 | Week 2 | Stage 2 | Deliverable
2.1.1 | Define effort estimation, RACI matrices, and project communications | Simple | 4 | Week 2 | Stage 2 | Completed
2.1.2 | Consolidate and baseline Report 2_PMP_BPG-CMS.docx | Medium | 6 | Week 2 | Stage 2 | Completed
2.2 | Report 3: SRS v0.9 (System Requirements Specification) |  | 25 | Week 2 | Stage 2 | Deliverable
2.2.1 | Map MVP features into customer requirements list | Complex | 8 | Week 2 | Stage 2 | Completed
2.2.2 | Define actor boundaries (Technical Manager, Project Leader) and use case diagrams | Medium | 7 | Week 2 | Stage 2 | Completed
2.2.3 | Consolidate core specifications into Report 3.0_SRS_BPG-CMS.docx | Complex | 10 | Week 2 | Stage 2 | Completed
2.3 | Vertical Prototypes & Infrastructure Setup Code and Document |  | 20 | Week 3 | Stage 2 | Deliverable
2.3.1 | Configure Gitflow, monorepo target layers, and backend service base foundations | Medium | 8 | Week 3 | Stage 2 | Completed
2.3.2 | Implement Vertical Spike: Connect .NET 8 backend service with React UI using Custom JWT | Complex | 12 | Week 3 | Stage 2 | Completed
Stage 3 | Software Design |  |  |  | Stage 3 | Section
3.1 | System Wireframing & Prototyping |  | 15 | Week 4 | Stage 3 | Deliverable
3.1.1 | Initially add some UI/UX interactive wireframes, some base flow (login, crud user,...) | Medium | 10 | Week 4 | Stage 3 | In Progress
3.1.2 | Collect and simulate sample data from the client to define the data used for simulation across different flows, or something similar. | Simple | 5 | Week 4 | Stage 3 | In Progress
3.2 | Report 4: SDS v1.0 (High-Level Design Specifications) |  | 20 | Week 4 | Stage 3 | Deliverable
3.2.1 | Design SQL Server schema (ERD, constraints) | Complex | 12 | Week 4 | Stage 3 | Completed
3.2.2 | Complete Software Design Specification (Report 4_SDS) – Class diagrams, sequence diagrams for core features | Medium | 8 | Week 4 | Stage 3 | In Progress
3.3 | Report 5: Test Planning |  | 10 | Week 5 | Stage 3 | Deliverable
3.3.1 | Formulate global test strategy and severity definitions (Report 5.0_Test Documentation.docx) | Complex | 10 | Week 5 | Stage 3 | In Progress
3.4 | Technical Environment Baseline |  | 15 | Week 5 | Stage 3 | Deliverable
3.4.1 | Setup Local/Staging Docker Containers (SQL Server, .NET backend service, React Images) | Complex | 15 | Week 5 | Stage 3 | In Progress
Stage 4 | Implementation |  |  |  | Stage 4 | Section
4.1 | Iteration 1: WBS Management, Progress Logs, CRUD Master Data |  | 50 | End of W7 | Stage 4 | Deliverable
4.1.1 | Update Detailed Architectural blueprints for WBS and Diary entities inside Report 4_SDS.docx | Simple | 3 | Week 6 | Stage 4 | Task
4.1.2 | Develop Database Schema, EF Core Migrations & Master Data Seeding Scripts | Medium | 5 | Week 6 | Stage 4 | Task
4.1.3 | Implement Global Error Handling Middleware & Centralized Logging System (Serilog) | Medium | 4 | Week 6 | Stage 4 | Task
4.1.4 | Code Features: WBS Tree Management, Mobile-Responsive Daily Progress Logs, CRUD master data | Complex | 16 | Week 6 | Stage 4 | Task
4.1.5 | Develop Unit Test Suites (xUnit Controllers & Core Domain Services Validation) | Medium | 6 | Week 6 | Stage 4 | Task
4.1.6 | Conduct Peer Review, Code Refactoring, and Pull Request Approvals | Simple | 3 | Week 6 | Stage 4 | Task
4.1.7 | Execute Component Integration Testing and document engineering bugs | Medium | 5 | Week 7 | Stage 4 | Task
4.1.8 | Refine technical constraints and update project tracking sheet | Simple | 3 | Week 7 | Stage 4 | Task
4.1.9 | Conduct Iteration 1 internal demo and finalize local environment testing | Simple | 5 | Week 7 | Stage 4 | Task
4.2 | Iteration 2: Virtual Inventory, Purchase Orders & Surplus Handling |  | 50 | End of W9 | Stage 4 | Deliverable
4.2.1 | Update Detailed Architectural blueprints for Stock and PO entities inside Report 4_SDS.docx | Simple | 3 | Week 8 | Stage 4 | Task
4.2.2 | Code Features: Virtual Site Inventory Tracking, BOQ Limit Validations, PO Logs, and Receipt Ingestion | Complex | 14 | Week 8 | Stage 4 | Task
4.2.3 | Code Features: Surplus Handling, Supplier Materials Return, and On-Site Liquidation Flow UI/backend service | Complex | 12 | Week 8 | Stage 4 | Task
4.2.4 | Develop Unit Test Suites (Verify virtual stock arithmetic calculations & workflow multi-states) | Medium | 6 | Week 8 | Stage 4 | Task
4.2.5 | Conduct Peer Review, Code Refactoring, and Pull Request Approvals | Simple | 3 | Week 8 | Stage 4 | Task
4.2.6 | Execute Component Integration Testing and document engineering bugs | Medium | 3 | Week 9 | Stage 4 | Task
4.2.7 | Refine technical constraints and update project tracking sheet | Simple | 4 | Week 9 | Stage 4 | Task
4.2.8 | Conduct Iteration 2 internal demo and finalize local environment testing | Medium | 5 | Week 9 | Stage 4 | Task
4.3 | Iteration 3: Management Dashboards, Admin feature, Incident Handling |  | 50 | End of W11 | Stage 4 | Deliverable
4.3.1 | Update Detailed Architectural blueprints for Analytics displays inside Report 4_SDS.docx | Simple | 3 | Week 10 | Stage 4 | Task
4.3.2 | Code Features: Incident & Error Handling Workflow, Admin CRUD features, & Executive Progress Charts | Complex | 16 | Week 10 | Stage 4 | Task
4.3.3 | Develop Unit Test Suites (Verify Incident multi-tier approval states & Dashboard Chart Ingestion Data) | Medium | 6 | Week 10 | Stage 4 | Task
4.3.4 | Conduct Peer Review, Final Global Code Refactoring, and Pull Request Approvals | Simple | 4 | Week 10 | Stage 4 | Task
4.3.5 | Execute Component Integration Testing for Incident Rework validations and chart renders | Medium | 5 | Week 10 | Stage 4 | Task
4.3.6 | Configure Automated Production Deployment Pipelines via GitHub Actions | Medium | 6 | Week 11 | Stage 4 | Task
4.3.7 | Merge all iteration branches, execute full system local run, and prepare release packages | Medium | 10 | Week 11 | Stage 4 | Task
Stage 5 | Verification & Validation |  |  |  | Stage 5 | Section
5.1 | Report 5: System Test Report (Execute Full End-to-End Multi-Role Validation & UAT) | Complex | 20 | Week 12 | Stage 5 | Deliverable
5.2 | Report 6: User Guides (System Installation Guide, Role-Based User Operation Manuals) | Medium | 8 | Week 12 | Stage 5 | Deliverable
5.2.1 | Execute Security Audits & Vulnerability Performance Load Testing (JMeter/request testing tool) | Medium | 8 | Week 13 | Stage 5 | Task
5.2.2 | Final Production Release Delivery (Docker Multi-Container Release, Automated DB Crontab Backups) | Complex | 12 | Week 13 | Stage 5 | Task
Stage 6 | Closing |  |  |  | Stage 6 | Section
6.1 | Report 7: Final Project Report (Synthesize full system lifecycle, execution results, and metrics) | Medium | 12 | Week 14 | Stage 6 | Deliverable
6.2 | Presentation File (Graduation thesis slides, system architecture posters, live demo script) | Medium | 8 | Week 14 | Stage 6 | Deliverable
TOTAL | TOTAL ESTIMATED EFFORT (PERSON-DAYS) |  | 345 | W15 Defense | Overall | Summary

## Iteration 1
PROJECT WORK BREAKDOWN STRUCTURE
ID | Use Case | Feature | Level* | Description | In Charge | Planned | Status | Actor
UC-001 | Login | Authentication | Medium | Authenticate with a registered account to access the system. | Tuấn | Iteration 1 | Testing | Common User
UC-002 | Forgot Password | Authentication | Medium | Request a password reset OTP through the registered email address. | Tuấn | Iteration 1 | Testing | Common User
UC-003 | View Profile | User Profile | Simple | View personal account and profile information. | Tuấn | Iteration 1 | Testing | Common User
UC-004 | Update Profile | User Profile | Medium | Update personal profile information such as name and contact details. | Tuấn | Iteration 1 | Testing | Common User
UC-005 | Logout | Authentication | Simple | End the current login session. | Tuấn | Iteration 1 | Testing | Common User
UC-006 | Change Password | Authentication | Medium | Change the current password after providing the existing password. | Tuấn | Iteration 1 | Testing | Common User
UC-007 | Reset Password | Authentication | Medium | Reset the account password using a valid OTP. | Tuấn | Iteration 1 | Testing | Common User
UC-008 | View List User | User Management | Simple | View and search the list of user accounts. | Tuấn | Iteration 1 | Testing | Admin
UC-009 | Create User | User Management | Medium | Create a new staff account and assign a system role. | Tuấn | Iteration 1 | Testing | Admin
UC-010 | Edit / Lock-Unlock User Account | User Management | Medium | Update user information or lock and unlock an account. | Tuấn | Iteration 1 | Testing | Admin
UC-011 | Delete User | User Management | Simple | Remove a user account from active use. | Tuấn | Iteration 1 | Testing | Admin
UC-012 | View System Configuration | System Configuration | Simple | View system configuration values used by the application. | Tuấn | Iteration 1 | Testing | Common User
UC-013 | Update System Configuration | System Configuration | Medium | Update configurable system values. | Tuấn | Iteration 1 | Testing | Admin
UC-014 | View Company Branding Information | System Configuration | Simple | View company name and branding information. | Tuấn | Iteration 1 | Testing | Common User
UC-015 | Update Company Name and Logo | System Configuration | Medium | Update the company name and logo used in the system. | Tuấn | Iteration 1 | Testing | Admin
UC-016 | View Notification List | Notification | Simple | View personal notifications. | Tuấn | Iteration 1 | Testing | Common User
UC-017 | Mark Notification as Read | Notification | Simple | Mark selected notifications as read. | Tuấn | Iteration 1 | Testing | Common User
UC-018 | View Category List | Material Master Data | Simple | View material category records. | Long | Iteration 1 | Testing | Admin
UC-019 | Add New Category | Material Master Data | Medium | Create a new material category. | Long | Iteration 1 | Testing | Admin
UC-020 | Update Category | Material Master Data | Medium | Update an existing material category. | Long | Iteration 1 | Testing | Admin
UC-021 | Delete Category | Material Master Data | Simple | Delete an existing material category. | Long | Iteration 1 | Testing | Admin
UC-022 | View Material List | Material Master Data | Simple | View material catalog records. | Long | Iteration 1 | Testing | Admin
UC-023 | Add New Material | Material Master Data | Medium | Create a new material catalog item. | Long | Iteration 1 | Testing | Admin
UC-024 | Update Material | Material Master Data | Medium | Update material catalog information. | Long | Iteration 1 | Testing | Admin
UC-025 | Delete Material | Material Master Data | Simple | Delete a material catalog item. | Long | Iteration 1 | Testing | Admin
UC-026 | Update Material Unit Conversion | Material Master Data | Medium | Update supported unit conversions for a material. | Long | Iteration 1 | Testing | Admin
UC-027 | View Supplier List | Supplier Management | Simple | View supplier records. | Đức | Iteration 1 | Testing | Admin, Project Leader, Accountant, Technical Manager, Director
UC-028 | Add New Supplier | Supplier Management | Medium | Create a new supplier record. | Đức | Iteration 1 | Testing | Accountant, Technical Manager, Director
UC-029 | Update Supplier | Supplier Management | Medium | Update supplier information. | Đức | Iteration 1 | Testing | Accountant, Technical Manager, Director
UC-030 | Delete Supplier | Supplier Management | Simple | Delete a supplier record. | Đức | Iteration 1 | Testing | Accountant, Technical Manager, Director
UC-031 | View Unit List | Unit Management | Simple | View measurement unit records. | Long | Iteration 1 | Testing | Admin
UC-032 | Add New Unit | Unit Management | Medium | Create a new measurement unit. | Long | Iteration 1 | Testing | Admin
UC-033 | Update Unit | Unit Management | Medium | Update a measurement unit. | Long | Iteration 1 | Testing | Admin
UC-034 | Delete Unit | Unit Management | Simple | Delete a measurement unit. | Long | Iteration 1 | Testing | Admin
UC-035 | View Executive Dashboard | Dashboard | Complex | View dashboard metrics and warnings according to the user's access scope. | Cường | Iteration 1 | Testing | Common User
UC-036 | View Project List | Project Management | Simple | View projects available to the user's role and project membership. | Cường | Iteration 1 | Testing | Technical Manager, Project Leader, Site Engineer, Director, Accountant
UC-037 | Create Project | Project Management | Medium | Create a new construction project. | Cường | Iteration 1 | Testing | Technical Manager
UC-038 | Update Project | Project Management | Medium | Update project information and planning data. | Cường | Iteration 1 | Testing | Technical Manager
UC-039 | Delete Project | Project Management | Simple | Delete a project from active use. | Cường | Iteration 1 | Testing | Technical Manager
UC-040 | View Project Details | Project Management | Simple | View detailed project information within the user's access scope. | Cường | Iteration 1 | Testing | Technical Manager, Project Leader, Site Engineer, Director, Accountant
UC-041 | Change Project Execution Status | Project Management | Medium | Activate, pause, or resume project execution according to role permissions. | Cường | Iteration 1 | Testing | Technical Manager, Director
UC-042 | Add Member to Project | Project Management | Medium | Add staff members to a project team. | Cường | Iteration 1 | Testing | Technical Manager
UC-043 | Remove Member from Project | Project Management | Simple | Remove staff members from a project team. | Cường | Iteration 1 | Testing | Technical Manager
UC-044 | Assign Project Leader | Project Management | Medium | Assign or change the project leader for a project. | Cường | Iteration 1 | Testing | Technical Manager
UC-045 | View and Interact with Design Drawings | Project Management | Simple | View and interact with project design drawings from the project workspace. | Cường | Iteration 1 | Testing | Technical Manager, Project Leader, Site Engineer, Director
UC-046 | View Project Work Chart (Gantt Chart) | Project Work Chart | Simple | View the project work schedule and task timeline. | Cường | Iteration 1 | Testing | Technical Manager, Project Leader, Site Engineer, Director
UC-052 | View Daily Log List | Daily Log | Simple | View daily logs for accessible projects or assigned work. | Đức | Iteration 1 | Testing | Technical Manager, Project Leader, Site Engineer, Director, Accountant
UC-053 | Create Daily Log | Daily Log | Complex | Create a daily construction log and update task progress. | Đức | Iteration 1 | Testing | Technical Manager, Project Leader, Assigned Site Engineer
UC-054 | Edit Daily Log | Daily Log | Medium | Edit an eligible daily construction log. | Đức | Iteration 1 | Testing | Technical Manager, Project Leader, Assigned Site Engineer
UC-055 | View Task Progress History | Daily Log | Simple | View progress changes history for a task. | Đức | Iteration 1 | Testing | Technical Manager, Project Leader, Site Engineer, Director
UC-056 | Add Comment to Daily Log | Daily Log | Medium | Add a discussion comment under a daily log. | Đức | Iteration 1 | Testing | Technical Manager, Project Leader, Site Engineer, Director
UC-057 | Update Own Comment on Daily Log | Daily Log | Medium | Update the user's own daily log comment. | Đức | Iteration 1 | Testing | Comment Author
UC-058 | Delete Comment | Daily Log | Simple | Delete the user's own daily log comment. | Đức | Iteration 1 | Testing | Comment Author
UC-097 | View WBS Tree | WBS & Task Management | Simple | View the project WBS hierarchy and task structure. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader, Site Engineer, Director, Accountant
UC-098 | Create Phase | WBS & Task Management | Medium | Create a project phase in the WBS. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader
UC-099 | Create Task | WBS & Task Management | Complex | Create a task under a project phase or parent task. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader
UC-100 | View Task Details | WBS & Task Management | Simple | View detailed task information. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader, Site Engineer, Director, Accountant
UC-101 | Update Task | WBS & Task Management | Medium | Update task information with required business validations. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader
UC-102 | Delete Task | WBS & Task Management | Simple | Delete a task from the WBS. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader
UC-103 | Assign Task | WBS & Task Management | Medium | Assign users to a task. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader
UC-104 | Update Phase | WBS & Task Management | Medium | Update project phase information. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader
UC-105 | Delete Phase | WBS & Task Management | Simple | Delete a project phase. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader
UC-106 | Mark Task Obsolete | WBS & Task Management | Simple | Mark a task as obsolete when it should no longer be executed. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader
UC-107 | Restore Task | WBS & Task Management | Medium | Restore an obsolete task back to active use. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader
UC-108 | Adjust Task Progress | WBS & Task Management | Medium | Manually adjust task progress. | Sơn | Iteration 1 | Testing | Technical Manager
UC-109 | Add Task Dependency | WBS & Task Management | Medium | Add a dependency between two tasks. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader
UC-110 | Remove Task Dependency | WBS & Task Management | Simple | Remove an existing task dependency. | Sơn | Iteration 1 | Testing | Technical Manager, Project Leader
UC-111 | View Phase Acceptance List | Phase Acceptance | Simple | View phase acceptance records for accessible projects. | Long | Iteration 1 | Testing | Admin, Technical Manager, Project Leader, Site Engineer, Director, Accountant
UC-112 | View Phase Acceptance Detail | Phase Acceptance | Simple | View detailed phase acceptance information. | Long | Iteration 1 | Testing | Technical Manager, Project Leader, Site Engineer, Director, Accountant
UC-113 | Perform Phase Acceptance | Phase Acceptance | Medium | Record acceptance of a completed phase and lock the related work. | Long | Iteration 1 | Testing | Technical Manager, Project Leader
UC-114 | Cancel Phase Acceptance | Phase Acceptance | Simple | Cancel an existing phase acceptance record and reopen related work. | Long | Iteration 1 | Testing | Technical Manager, Project Leader

## Iteration 2
PROJECT WORK BREAKDOWN STRUCTURE
ID | Use Case | Feature | Level* | Description | In Charge | Planned | Status | Actor
UC-047 | Create Purchase Order | Purchase Order | Complex | Create a purchase order from approved material requests. | Tuấn | Iteration 2 | Debugging | Accountant
UC-048 | View Purchase Order List | Purchase Order | Simple | View purchase orders, with project/member filtering applied where required. | Tuấn | Iteration 2 | Debugging | Accountant, Technical Manager, Site Engineer, Director
UC-049 | Cancel Purchase Order | Purchase Order | Simple | Cancel an eligible purchase order. | Tuấn | Iteration 2 | Debugging | Accountant
UC-050 | View Purchase Order Detail | Purchase Order | Simple | View detailed purchase order information. | Tuấn | Iteration 2 | Debugging | Accountant, Technical Manager, Site Engineer, Director
UC-051 | Close Purchase Order | Purchase Order | Simple | Close a completed or no-longer-needed purchase order. | Tuấn | Iteration 2 | Debugging | Accountant
UC-065 | View List Material BOQ | BOQ Management | Simple | View approved BOQ material items for a phase. | Long | Iteration 2 | Debugging | Site Engineer, Technical Manager, Admin
UC-066 | Update List Material BOQ | BOQ Management | Medium | Update BOQ material items for a phase. | Long | Iteration 2 | Debugging | Technical Manager
UC-067 | View Material Request List | Material Request | Simple | View material requests within the user's role and project scope. | Long | Iteration 2 | Debugging | Admin, Director, Technical Manager, Accountant, Project Leader
UC-068 | Create Material Request | Material Request | Complex | Create a material request for a project phase. | Long | Iteration 2 | Debugging | Project Leader
UC-069 | Resubmit Material Request | Material Request | Medium | Revise and resubmit a rejected material request. | Long | Iteration 2 | Debugging | Project Leader
UC-070 | Cancel Material Request | Material Request | Simple | Cancel an eligible material request. | Long | Iteration 2 | Debugging | Project Leader
UC-071 | Review and Submit Material Request | Material Request | Medium | Review a material request and submit it for the next approval step. | Long | Iteration 2 | Debugging | Accountant
UC-072 | Review Material Request (Over-BOQ) | Material Request | Medium | Approve or reject material requests that exceed BOQ limits. | Long | Iteration 2 | Debugging | Director
UC-073 | View Site Inventory | Inventory | Simple | View current project inventory balances. | Đức | Iteration 2 | Debugging | Director, Technical Manager, Accountant, Project Member
UC-074 | Receive Goods | Goods Receipt | Complex | Record received goods against an eligible purchase order and update inventory. | Đức | Iteration 2 | Debugging | Technical Manager, Project Leader
UC-075 | View Goods Receipt List | Goods Receipt | Simple | View goods receipt records for accessible projects. | Đức | Iteration 2 | Debugging | Director, Technical Manager, Accountant, Project Member
UC-076 | View Goods Receipt Detail | Goods Receipt | Simple | View detailed information for a goods receipt. | Đức | Iteration 2 | Debugging | Director, Technical Manager, Accountant, Project Member
UC-077 | Cancel Goods Receipt | Goods Receipt | Simple | Cancel an eligible goods receipt and reverse inventory effects. | Đức | Iteration 2 | Debugging | Admin, Technical Manager, Accountant, Director
UC-078 | Edit Goods Receipt Metadata | Goods Receipt | Medium | Edit non-stock metadata of a goods receipt. | Đức | Iteration 2 | Debugging | Admin, Technical Manager, Accountant, Director
UC-079 | Create Material Issuance | Material Issuance | Complex | Create a material issuance and decrease project inventory. | Đức | Iteration 2 | Debugging | Technical Manager
UC-080 | View Material Issuance List | Material Issuance | Simple | View material issuance records for accessible projects. | Đức | Iteration 2 | Debugging | Director, Technical Manager, Accountant, Project Member
UC-081 | View Material Issuance Detail | Material Issuance | Simple | View detailed information for a material issuance. | Đức | Iteration 2 | Debugging | Director, Technical Manager, Accountant, Project Member
UC-082 | View Inventory Transaction List | Inventory | Simple | View inventory transaction history for accessible projects. | Đức | Iteration 2 | Debugging | Director, Technical Manager, Accountant, Project Member
UC-083 | Create Material Return | Material Return | Complex | Create a material return and increase project inventory. | Đức | Iteration 2 | Debugging | Technical Manager
UC-084 | View Material Return List | Material Return | Simple | View material return records for accessible projects. | Đức | Iteration 2 | Debugging | Director, Technical Manager, Accountant, Project Member
UC-085 | View Material Return Detail | Material Return | Simple | View detailed information for a material return. | Đức | Iteration 2 | Debugging | Director, Technical Manager, Accountant, Project Member
UC-086 | View Inventory Adjustments List | Inventory Adjustment | Simple | View inventory adjustment records for accessible projects. | Cường | Iteration 2 | Debugging | Director, Technical Manager, Accountant, Project Member
UC-087 | Create Inventory Increase Adjustment | Inventory Adjustment | Medium | Create an adjustment that increases inventory stock. | Cường | Iteration 2 | Debugging | Technical Manager, Project Leader, Admin, Site Engineer
UC-088 | Create Inventory Decrease Adjustment | Inventory Adjustment | Medium | Create an adjustment request that decreases inventory stock. | Cường | Iteration 2 | Debugging | Accountant, Admin
UC-089 | Approve/Reject Inventory Decrease Adjustment | Inventory Adjustment | Medium | Approve or reject an inventory decrease adjustment. | Cường | Iteration 2 | Debugging | Director, Admin
UC-115 | View List of Direct Purchase Requests | Direct Purchase | Simple | View direct purchase requests within the user's access scope. | Tuấn | Iteration 2 | Debugging | Technical Manager, Site Engineer, Accountant, Admin
UC-116 | View Direct Purchase Request Detail | Direct Purchase | Simple | View detailed information for a direct purchase request. | Tuấn | Iteration 2 | Debugging | Technical Manager, Site Engineer, Accountant, Admin
UC-117 | Create Direct Purchase Request | Direct Purchase | Complex | Create a direct purchase request for urgent or out-of-flow procurement. | Tuấn | Iteration 2 | Debugging | Site Engineer
UC-118 | Audit Direct Purchase Request | Direct Purchase | Medium | Audit and process a direct purchase request. | Tuấn | Iteration 2 | Debugging | Accountant
UC-119 | Create Surplus Request | Surplus Management | Complex | Create a surplus material request for a project. | Sơn | Iteration 2 | Debugging | Technical Manager, Site Engineer, Admin
UC-120 | View Surplus Request List | Surplus Management | Simple | View surplus material requests. | Sơn | Iteration 2 | Debugging | Technical Manager, Accountant, Site Engineer, Project Leader, Admin
UC-121 | View Surplus Request Detail | Surplus Management | Simple | View detailed surplus request information. | Sơn | Iteration 2 | Debugging | Technical Manager, Accountant, Site Engineer, Project Leader, Admin
UC-122 | Liquidate Surplus Material | Surplus Management | Medium | Create a liquidation action for surplus material. | Sơn | Iteration 2 | Debugging | Accountant
UC-123 | Return Surplus Material | Surplus Management | Medium | Create a return-to-stock action for surplus material. | Sơn | Iteration 2 | Debugging | Accountant
UC-124 | View Surplus Action List | Surplus Management | Simple | View actions recorded for a surplus request item. | Sơn | Iteration 2 | Debugging | Technical Manager, Accountant, Site Engineer, Project Leader, Admin
UC-125 | Propose Surplus Transfer | Surplus Management | Complex | Propose transferring surplus material to another project. | Sơn | Iteration 2 | Debugging | Site Engineer, Project Leader, Technical Manager, Admin
UC-126 | Review Surplus Transfer | Surplus Management | Medium | Approve or reject a proposed surplus transfer. | Sơn | Iteration 2 | Debugging | Technical Manager
UC-127 | Dispatch Surplus Transfer | Surplus Management | Medium | Dispatch approved surplus material from the source project. | Sơn | Iteration 2 | Debugging | Project Leader, Technical Manager
UC-128 | View Incoming Transfers | Surplus Management | Simple | View incoming surplus transfers for a destination project. | Sơn | Iteration 2 | Debugging | Project Leader, Technical Manager
UC-129 | Receive Surplus Transfer | Surplus Management | Complex | Receive dispatched surplus material into the destination project inventory. | Sơn | Iteration 2 | Debugging | Project Leader, Technical Manager
UC-130 | Close Remaining Surplus Material | Surplus Management | Simple | Allows the Technical Manager or Admin to stop processing the remaining quantity of a material item while leaving its physical warehouse stock unchanged. | Sơn | Iteration 2 | Debugging | Technical Manager, Director

## Iteration 3
PROJECT WORK BREAKDOWN STRUCTURE
ID | Use Case | Feature | Level* | Description | In Charge | Planned | Status | Actor
UC-059 | View Incidents List | Incident Management | Simple | View incident reports within the user's access scope. | Cường | Iteration 3 | Debugging | Technical Manager, Admin, Accountant, Director, Project Member
UC-060 | Report Construction Incident | Incident Management | Medium | Report a construction-related incident for a project. | Cường | Iteration 3 | Debugging | Site Engineer, Technical Manager, Admin
UC-061 | Report Emergency Stop Incident | Incident Management | Medium | Report an emergency incident that may pause project execution. | Cường | Iteration 3 | Debugging | Site Engineer, Technical Manager, Admin
UC-062 | Resolve Construction Incident | Incident Management | Medium | Confirm or reject resolution of a construction incident. | Cường | Iteration 3 | Debugging | Technical Manager, Admin, Accountant, Director
UC-063 | Report Inventory Incident | Incident Management | Medium | Report an inventory-related incident. | Cường | Iteration 3 | Debugging | Site Engineer, Technical Manager, Admin
UC-064 | Verify and Approve Inventory Incident | Incident Management | Medium | Review and approve or reject an inventory incident. | Cường | Iteration 3 | Debugging | Technical Manager, Admin, Accountant, Director
UC-090 | View Project Executive Dashboard (Overview) | Reports | Complex | View project overview indicators and executive summary data. | Cường | Iteration 3 | Debugging | Director, Admin
UC-091 | View Project Construction Progress Report | Reports | Complex | View construction progress report data for a project. | Cường | Iteration 3 | Debugging | Director, Accountant
UC-092 | View Project BOQ vs Actual Report | Reports | Complex | Compare project BOQ quantities with actual usage. | Cường | Iteration 3 | Debugging | Director, Accountant
UC-093 | View Project Incident Summary Report | Reports | Simple | View summarized project incident statistics and details. | Cường | Iteration 3 | Debugging | Director, Accountant
UC-094 | View Project Inventory Ledger Report | Reports | Simple | View inventory ledger movements for a project. | Cường | Iteration 3 | Debugging | Director, Accountant
UC-095 | View Project Procurement and Cost Report | Reports | Complex | View procurement and cost report data for a project. | Cường | Iteration 3 | Debugging | Director, Accountant
UC-096 | View Portfolio Dashboard (All Projects) | Reports | Complex | View consolidated indicators across projects available to the user's role. | Cường | Iteration 3 | Debugging | Director, Accountant

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32

## Defects
PROJECT DEFECTS
# | Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)